## Sheet1
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Project Introduction & Planning | bar: Week 1
Requirement Gathering & Documentation | bar: Week 2
UI Design (Figma) | bar: Week 3
ERD & Schema Design | bar: Week 4
Flutter Development | bar: Week 5 to Week 6
Database Integration | bar: Week 7 to Week 8
Testing | bar: Week 9 to Week 10
Deployment & Final Report | bar: Week 11 to Week 12